## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a…. I want to ….. So that I can …. | Task 1 | Supriksha | Write a program for displaying the Login | 5 | New Estimates of Effort remaining at end of Day1: 4; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Huda | Design and create the DB fields | 4 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 1 | In Progress
|  | Task 3 | Vivek | Write a program for displaying the homepage | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 | Parikshith | Write a program for conneting Database | 3 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 3 | Open
|  | Task 5 |  | ---- | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | Open
|  | … | … | ---- | --
|  | Task n | … | Execute the tests | --
US002 | As a…. I want to ….. So that I can …. | Task 1 | Lakshmi | ---- | 6 | New Estimates of Effort remaining at end of Day1: 6; New Estimates of Effort remaining at end of Day2: 6; New Estimates of Effort remaining at end of Day3: 6 | Open
|  | Task 2 | Priti | ---- | 5 | New Estimates of Effort remaining at end of Day1: 5; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | Ninad | ---- | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 2 | In Progress
|  | Task 4 | John | ---- | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | … | … | ---- | --
|  | Task n | … | ---- | --
….. |  |  |  |  | --
US014 |  |  |  |  | --
|  |  |  | Total | 300 | New Estimates of Effort remaining at end of Day1: 260; New Estimates of Effort remaining at end of Day2: 220; New Estimates of Effort remaining at end of Day3: 160

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
300 | 260 | 220 | 160 | 90 | 65 | 0
300 | 250 | 200 | 150 | 100 | 50 | 0