## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | Login Page | Task 1 | Parikshith | Write a Flask program to display the login page | 4 | 4 | 4 | 3 | 3 | 1 | 0 | closed
|  | Task 2 | Vivek | Design the UI for the Login Page | 4 | 4 | 4 | 3 | 2 | 0 | 0 | closed
|  | Task 3 | Supriksha | Design and create the DB Login fields | 2 | 2 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 4 | Sheri | Design the UI for the Login Page | 3 | 3 | 3 | 2 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | Write a query to login | 3 | 3 | 3 | 2 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 1 | 1 | 1 | 1 | 1 | 1 | 0 | closed
US002 | Logout Page | Task 1 | Parikshith | Write a Flask program to logout from a customer account | 4 | 4 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 2 | Vivek | Design the UI for the login Page | 4 | 4 | 2 | 1 | 0 | 0 | 0 | closed
|  | Task 3 | Supriksha | Design and create the DB Login fields | 4 | 4 | 2 | 1 | 0 | 0 | 0 | closed
|  | Task 4 | Sheri | Design and create the DB Login fields | 4 | 4 | 3 | 1 | 0 | 0 | 0 | Closed
|  | Task 5 | Huda | Design the UI for the Logout Page | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
US003 | Dashboard design | Task 1 | Parikshith | Write a Flask program to display the page | 3 | 3 | 3 | 2 | 1 | 0 | 0 | closed
|  | Task 2 | Vivek | Javascript part of the dashborad | 5 | 5 | 4 | 3 | 2 | 0 | 0 | closed
|  | Task 3 | Supriksha | Design and create the DB tables | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 4 | Sheri | Javascript part of the dashborad | 5 | 4 | 3 | 2 | 1 | 0 | 0 | closed
|  | Task 5 | Huda | queries for inserting customer details into db | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | CSS Buttons | 4 | 3 | 2 | 1 | 0 | 0 | 0 | closed
US004 | Add customer | Task 1 | Parikshith | Write a Flask program to add customer to db | 5 | 5 | 3 | 3 | 2 | 1 | 0 | closed
|  | Task 2 | Vivek | Javascript part of the dashborad | 5 | 5 | 3 | 3 | 1 | 0 | 0 | closed
|  | Task 3 | Supriksha | Design and create the DB tables | 3 | 3 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 4 | Sheri | Javascript part of the dashborad | 4 | 4 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | Query to add customer and error handling | 3 | 3 | 2 | 2 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 2 | 2 | 1 | 1 | 1 | 0 | 0 | closed
US006 | Search customer | Task 1 | Parikshith | Write a Flask program to search customer in db | 4 | 4 | 1 | 1 | 1 | 1 | 0 | closed
|  | Task 2 | Vivek | Javascript part of the dashborad | 3 | 3 | 1 | 1 | 0 | 0 | 0 | closed
|  | Task 3 | Supriksha | CSS hover effects | 3 | 3 | 2 | 2 | 2 | 1 | 0 | closed
|  | Task 4 | Sheri | Javascript part of the dashborad | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | query to search customer and error handling | 2 | 2 | 1 | 1 | 1 | 0 | 0 | closed
|  | Task 6 | Gobind | CSS buttons | 2 | 2 | 1 | 1 | 1 | 0 | 0 | closed
US007 | Update customer | Task 1 | Parikshith | Write a Flask program to update customer to db | 3 | 3 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 2 | Vivek | Dropdown for dashboard | 3 | 3 | 1 | 1 | 1 | 1 | 0 | closed
|  | Task 3 | Supriksha | CSS for login page | 3 | 3 | 2 | 2 | 2 | 2 | 0 | closed
|  | Task 4 | Sheri | CSS for login page | 3 | 3 | 2 | 2 | 2 | 1 | 0 | closed
|  | Task 5 | Huda | query to update customer and error handling | 2 | 2 | 2 | 2 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | CSS Buttons | 2 | 2 | 2 | 2 | 1 | 1 | 0 | closed
US008 | Delete customer | Task 1 | Parikshith | Write a Flask program to delete customer in db | 3 | 3 | 2 | 2 | 2 | 1 | 0 | closed
|  | Task 2 | Vivek | Dropdown for dashboard | 3 | 3 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 3 | Supriksha | CSS for login page | 3 | 3 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 4 | Sheri | CSS for login page | 2 | 2 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 5 | Huda | query to delete customer and error handling | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 2 | 2 | 2 | 1 | 1 | 1 | 0 | closed
US009 | Add account | Task 1 | Parikshith | Write a Flask program to add account to db | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 2 | Vivek | CSS for Dashboard | 3 | 3 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 3 | Supriksha | CSS for login page | 2 | 2 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 4 | Sheri | Keyframes css | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | query to add account and error handling | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 1 | 1 | 1 | 1 | 1 | 1 | 0 | closed
US010 | Delete account | Task 1 | Parikshith | Write a Flask program to delete account in db | 3 | 3 | 2 | 0 | 1 | 1 | 0 | closed
|  | Task 2 | Vivek | displaying tables , css for tables | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 3 | Supriksha | Execute the tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
|  | Task 4 | Sheri | webkit keyframes css | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | query to delete account and error handling | 2 | 2 | 0 | 0 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | media-css | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
US0011 | Search account | Task 1 | Parikshith | Write a Flask program to search account in db | 3 | 3 | 2 | 0 | 0 | 0 | 0 | closed
|  | Task 2 | Vivek | CSS | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 3 | Supriksha | CSS | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 4 | Sheri | On front end to give search option | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | query to search account and error handling | 2 | 2 | 1 | 0 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
US0012 | Deposit in an account | Task 1 | Parikshith | Write a Flask program to deposit account in db | 3 | 3 | 2 | 1 | 0 | 0 | 0 | closed
|  | Task 2 | Vivek | Dashboard-html | 2 | 2 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 3 | Supriksha | query to search account and error handling | 2 | 2 | 1 | 1 | 1 | 1 | 0 | closed
|  | Task 4 | Sheri | Dashboard-html | 2 | 2 | 2 | 1 | 1 | 1 | 0 | closed
|  | Task 5 | Huda | query to search account and error handling | 2 | 2 | 2 | 1 | 0 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
US0013 | Credit from the account | Task 1 | Parikshith | Write a Flask program to get amount from an account | 3 | 3 | 2 | 2 | 1 | 0 | 0 | closed
|  | Task 2 | Vivek | CSS dashboard | 3 | 3 | 2 | 2 | 2 | 1 | 0 | closed
|  | Task 3 | Supriksha | CSS dashboard | 3 | 3 | 2 | 2 | 2 | 2 | 0 | closed
|  | Task 4 | Sheri | CSS dashboard | 3 | 3 | 3 | 2 | 2 | 1 | 0 | closed
|  | Task 5 | Huda | Execute the tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
|  | Task 6 | Gobind | Query and error handling | 3 | 3 | 3 | 2 | 1 | 0 | 0 | closed
US0014 | Tranfer money through account | Task 1 | Parikshith | Flask program to transfer amount to a account | 4 | 4 | 4 | 4 | 3 | 2 | 0 | closed
|  | Task 2 | Vivek | frontend-option to transfer | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
|  | Task 3 | Supriksha | CSS | 3 | 3 | 3 | 3 | 2 | 1 | 0 | closed
|  | Task 4 | Sheri | query to transfer amount from one account to another | 2 | 2 | 2 | 1 | 0 | 0 | 0 | closed
|  | Task 5 | Huda | Execute the tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | closed
|  | Task 6 | Gobind | query to transfer amount from one account to another | 3 | 3 | 3 | 2 | 2 | 0 | 0 | closed
US0015 | Account status | Task 1 | Parikshith | displaying account status on frontend | 3 | 3 | 3 | 3 | 1 | 0 | 0 | closed
|  | Task 2 | Vivek | Write a Flask program for account status in db | 2 | 2 | 2 | 2 | 2 | 1 | 0 | closed
|  | Task 3 | Supriksha | CSS part for displaying | 3 | 3 | 3 | 3 | 3 | 3 | 0 | closed
|  | Task 4 | Sheri | CSS part for displaying | 4 | 4 | 4 | 3 | 2 | 2 | 0 | closed
|  | Task 5 | Huda | query to delete account and error handling | 3 | 3 | 3 | 3 | 2 | 0 | 0 | closed
|  | Task 6 | Gobind | Execute the tests | 3 | 3 | 3 | 3 | 2 | 1 | 0 | closed
US0016 | Account statement to display with PDF download option | Task 1 | Parikshith | Execute the tests | 4 | 4 | 4 | 4 | 3 | 0 | 0 | closed
|  | Task 2 | Vivek | displaying customer status on frontend-html | 2 | 2 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 3 | Supriksha | Write a Flask program to search account in db | 4 | 4 | 4 | 3 | 2 | 0 | 0 | closed
|  | Task 4 | Sheri | Write a Flask program to search account in db | 4 | 4 | 4 | 4 | 2 | 0 | 0 | closed
|  | Task 5 | Huda | displaying customer status on frontend | 2 | 2 | 2 | 2 | 1 | 0 | 0 | closed
|  | Task 6 | Gobind | Write a Flask program to search account in db | 2 | 2 | 2 | 2 | 1 | 0 | 0 | closed
US0017 | Customer status | Task 1 | Parikshith | Execute the tests | 2 | 2 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 2 | Vivek | CSS and HTML | 2 | 2 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 3 | Supriksha | Execute the tests | 2 | 2 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 4 | Sheri | CSS and HTML | 2 | 2 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 5 | Huda | CSS and HTML | 2 | 2 | 2 | 2 | 2 | 0 | 0 | closed
|  | Task 6 | Gobind | Write a Flask program to search account in db | 2 | 2 | 2 | 0 | 0 | 0 | 0 | closed
|  |  |  | Total | 265 | 263 | 202 | 141 | 103 | 51 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
300 | 260 | 220 | 160 | 90 | 65 | 0
300 | 250 | 200 | 150 | 100 | 50 | 0